## Assumptions
Group by Workpackage | Assumption start point | Assumption end point | Assumption | Assumption type
Work Package 1 Market Intelligence | OUTPUT - 1.0.1. High quality, relevant research is completed | OUTPUT - 1.0.2. Evidence-informed discussions facilitated | No major disruptions in budget and human resources for WP1 partners | New or improved conditions make it possible to act
Work Package 1 Market Intelligence | OUTPUT - 1.0.2. Evidence-informed discussions facilitated | EOI - 4. Transdisciplinary teams across CGIAR and partners co-implement market and behavioral intelligence and co-design of target product profiles | No major disruptions in budget and human resources for WP1 partners | New or improved conditions make it possible to act
Work Package 2 Target Product Profile Design | OUTPUT - 2.1.2 2.2.2.Gender-intentional target product profile | OUTPUT - 4.1.2., 4.2.2. Pipeline investment cases | Inclusive target product profiles support the development of pipeline investment cases | New or improved knowledge/technology makes it possible to act
Work Package 2 Target Product Profile Design | OUTPUT - 2.1.2 2.2.2.Gender-intentional target product profile | OUTCOME - 2.2. CGIAR and National partners breeding programs use Target Product Profiles (TPP's) for breeding decisions | Funding, a clear engagement process, institutional standards and processes, and a shared commitment towards increasing impacts of genetic innovation encourages the formation of regional, transdisciplinary CGIAR-NARES-SME teams in the co-design of product profiles. | Actor is convinced to act
Work Package 3 Behavioral Intelligence | OUTPUT - 3.1.1. Behavioural intelligence for accelerating varietal turnover | OUTCOME - 3.1. Seed systems actors share behavioral intelligence on how to accelerate varietal turnover with others in their institutions | Through strong engagement in the design of behavioral research, regional, transdisciplinary CGIAR-NARES-SME teams co-own behavioral intelligence and the value of the latter persuades them to use it in their strategies to accelerate varietal turnover. | Actor is convinced to act
Work Package 3 Behavioral Intelligence | OUTPUT - 3.1.1. Behavioural intelligence for accelerating varietal turnover | OUTPUT - 4.1.2., 4.2.2. Pipeline investment cases | Behavioral intelligence supports the development of pipeline investment cases. | New or improved knowledge/technology makes it possible to act
Work Package 3 Behavioral Intelligence | OUTPUT - 3.1.1. Behavioural intelligence for accelerating varietal turnover | OUTPUT - 2.1.2 2.2.2.Gender-intentional target product profile | Behavioral intelligence supports the development of inclusive product profiles. | New or improved knowledge/technology makes it possible to act
Work Package 3 Behavioral Intelligence | OUTPUT - 3.1.3., 3.2.3., 3.3.3. Global Behavioral intelligence based on meta-analysis and synthesis | OUTCOME - 3.2.Private sector and NGOs co-design strategies to address supply-side constraints to promoting new varieties and related products | Partners find value in the synthesis of findings across different settings because it strengthens evidence on how to accelerate turnover thanks to the external validity from replication in multiple settings. | New or improved knowledge/technology makes it possible to act
Work Package 3 Behavioral Intelligence | OUTPUT - 3.1.3., 3.2.3., 3.3.3. Global Behavioral intelligence based on meta-analysis and synthesis | OUTCOME - 3.1. Seed systems actors share behavioral intelligence on how to accelerate varietal turnover with others in their institutions | Partners find value in the synthesis of findings across different settings because it strengthens evidence on how to accelerate turnover thanks to the external validity from replication in multiple settings. | New or improved knowledge/technology makes it possible to act
Work Package 3 Behavioral Intelligence | OUTPUT - 3.1.3., 3.2.3., 3.3.3. Global Behavioral intelligence based on meta-analysis and synthesis | OUTCOME - 3.3. CGIAR and partners design research projects of high quality leading to rigorous behavioural intelligence | Newly created global behavior intelligence is addressing CGIAR partners knowledge gaps | Actor is convinced to act
Work Package 3 Behavioral Intelligence | OUTPUT - 3.2.2. Behavioural intelligence for promoting new products | OUTCOME - 3.2.Private sector and NGOs co-design strategies to address supply-side constraints to promoting new varieties and related products | Behavioral intelligence for promoting new products helps private sector and NGOs demonstrate value-for-money and increase investments in accelerating varietal turnover. | New or improved knowledge/technology makes it possible to act
Work Package 4 Pipeline Investment Cases | OUTPUT - 4.1.2., 4.2.2. Pipeline investment cases | OUTCOME - 4.1. CGIAR-NARES-SME breeding networks implement breeding pipelines that are aligned to the five Impact Areas | Strong engagement with Accelerated Breeding and clear demonstration of the value of pipeline investment cases convince breeders to refocus and restructure their pipelines and align them to the five impact areas, driven by a shared interest in maximizing the impact of breeding programs. | New or improved knowledge/technology makes it possible to act
Work Package 4 Pipeline Investment Cases | OUTPUT - 4.1.3., 4.2.3. Global Market Intelligence Platform (GloMIP) | OUTCOME - 4.2.CGIAR breeders use GloMIP and the Investor Dashboard to align breeding pipeline investment efforts commensurate to Impact Opportunities, Projected Benefits, and Returns on Investment across the five Impact Areas | Strong engagement with end-users and clear demonstration of returns on investment encourages research leaders and investors to use the Investor Dashboard in investment and resource allocation decision making in genetic innovations. | New or improved knowledge/technology makes it possible to act
Work Package 4 Pipeline Investment Cases | OUTPUT - 4.1.3., 4.2.3. Global Market Intelligence Platform (GloMIP) | OUTCOME - 2.2. CGIAR and National partners breeding programs use Target Product Profiles (TPP's) for breeding decisions | The Global Market Intelligence Platform enables CGIAR and partners to find market intelligence and design target product profiles, which will empower the teams. | New or improved knowledge/technology makes it possible to act
Work Package 5 Institutional Scaling and MELIA | OUTPUT - 5.1.5. Study to understand how MI influences investment in breeding pipelines | OUTCOME - 5.1 CGIAR-NARES-SME breeding networks’ knowledge enhanced on the contribution of institutional change in genetic innovation to the five impact areas | Clear indication of impacts triggers the interest of CGIAR-NARES-SME breeding networks in enhancing their knowledge on the contributions of institutional change in genetic innovation to the five impact areas, driven by a shared interest in maximizing the impact of breeding programs | Actor is convinced to act
Work Package 5 Institutional Scaling and MELIA | OUTPUT - 5.1.6. Study on the potential impact of different degrees of market smart varieties (across the 5 impact areas) | OUTCOME - 5.1 CGIAR-NARES-SME breeding networks’ knowledge enhanced on the contribution of institutional change in genetic innovation to the five impact areas | Clear indication of impacts triggers the interest of CGIAR-NARES-SME breeding networks in enhancing their knowledge on the contributions of institutional change in genetic innovation to the five impact areas, driven by a shared interest in maximizing the impact of breeding programs | Actor is convinced to act
Work Package 5 Institutional Scaling and MELIA | OUTPUT - 5.1.7. Adaptive planning | OUTCOME - 5.1 CGIAR-NARES-SME breeding networks’ knowledge enhanced on the contribution of institutional change in genetic innovation to the five impact areas | Clear indication of impacts triggers the interest of CGIAR-NARES-SME breeding networks in enhancing their knowledge on the contributions of institutional change in genetic innovation to the five impact areas, driven by a shared interest in maximizing the impact of breeding programs | Actor is convinced to act
Work Package 2 Target Product Profile Design | OUTCOME - 2.2. CGIAR and National partners breeding programs use Target Product Profiles (TPP's) for breeding decisions | EOI - 1. CGIAR and national partners share institutional standards & market and behavioral intelligence | The institutional innovation in the regional CGIAR-NARES-SME breeding networks improves relationships between CGIAR and partners, which motives them to scale the innovations. | New or improved relationships make it possible to act
Work Package 3 Behavioral Intelligence | OUTCOME - 3.1. Seed systems actors share behavioral intelligence on how to accelerate varietal turnover with others in their institutions | EOI - 1. CGIAR and national partners share institutional standards & market and behavioral intelligence | Partners find value in shared knowledge on behavioural intelligence and decide to apply in their operations. | Actor is empowered to act
Work Package 3 Behavioral Intelligence | OUTCOME - 3.2.Private sector and NGOs co-design strategies to address supply-side constraints to promoting new varieties and related products | EOI - 3. Seed industry and NGOs use market and behavioral intelligence | The behavioral intelligence is of such quality that it motivates the seed industry, food industry, and NGOs to use it in strategic decision making. | New or improved knowledge/technology makes it possible to act
Work Package 3 Behavioral Intelligence | OUTCOME - 3.3. CGIAR and partners design research projects of high quality leading to rigorous behavioural intelligence | EOI - 4. Transdisciplinary teams across CGIAR and partners co-implement market and behavioral intelligence and co-design of target product profiles | CGIAR Transdisciplinary teams use knowledge on behavioural intelligence when co-designing TPPs and strategies to promote these products' use. | New or improved knowledge/technology makes it possible to act
Work Package 4 Pipeline Investment Cases | OUTCOME - 4.1. CGIAR-NARES-SME breeding networks implement breeding pipelines that are aligned to the five Impact Areas | EOI - 1. CGIAR and national partners share institutional standards & market and behavioral intelligence | Demonstrated cases of CGIAR breeding programs refocusing and restructuring pipelines convince partners to adopt institutional standards | Actor is convinced to act
Work Package 4 Pipeline Investment Cases | OUTCOME - 4.2.CGIAR breeders use GloMIP and the Investor Dashboard to align breeding pipeline investment efforts commensurate to Impact Opportunities, Projected Benefits, and Returns on Investment across the five Impact Areas | EOI - 2. Research leaders and investors make investment decisions in genetic innovation using GloMIP and the Investor Dashboard | Positive user experience with the Investor Dashboard motivates research leaders and investors to adjust their investment and resource allocation decision making in genetic innovation, motivated by a strong drive to increase returns on their investments | Actor is empowered to act
| EOI - 1. CGIAR and national partners share institutional standards & market and behavioral intelligence | AA - Genetic Innovation | The adoption of institutional standards motivates public and private sector partners to increase collaboration, driven by a common interest in accelerating the rate of varietal adoption. | New or improved relationships make it possible to act
| EOI - 2. Research leaders and investors make investment decisions in genetic innovation using GloMIP and the Investor Dashboard | AA - Genetic Innovation | Improved investment decisions support the development and scaling of innovations that contribute to the empowerment of women, youth, and other social groups. | New or improved knowledge/technology makes it possible to act
| EOI - 2. Research leaders and investors make investment decisions in genetic innovation using GloMIP and the Investor Dashboard | AA - Genetic Innovation | Pipeline Investment Cases and the Investor Dashboard encourage CGAR-NARES-SME networks to use benefits assessment to refocus variety development with the aim of increasing impacts across the 5 Impact Areas. | Actor is empowered to act
| EOI - 2. Research leaders and investors make investment decisions in genetic innovation using GloMIP and the Investor Dashboard | AA - Genetic Innovation | Improved investment decisions will encourage CGIAR and partners to further strengthen the collaboration. | New or improved relationships make it possible to act
| EOI - 4. Transdisciplinary teams across CGIAR and partners co-implement market and behavioral intelligence and co-design of target product profiles | AA - Genetic Innovation | The transdisciplinary teams improve relationships between CGIAR, NARES and SMEs and encourages CGAR-NARES-SME networks to use market intelligence to refocus variety development with the aim of increasing impacts across the 5 Impact Areas. | New or improved relationships make it possible to act
| AA - Genetic Innovation | IA - Gender Equality, Youth and Social Inclusion | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Climate Adaptation and Mitigation | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Environmental Health and Biodiversity | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Poverty Reduction, Livelihoods and Jobs | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Nutrition, Health and Food Security | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Gender Equality, Youth and Social Inclusion | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Poverty Reduction, Livelihoods and Jobs | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Climate Adaptation and Mitigation | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Environmental Health and Biodiversity | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Nutrition, Health and Food Security | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Gender Equality, Youth and Social Inclusion | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Environmental Health and Biodiversity | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Nutrition, Health and Food Security | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Climate Adaptation and Mitigation | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Poverty Reduction, Livelihoods and Jobs | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this Impact Area. | New or improved knowledge/technology makes it possible to act
| IA - Climate Adaptation and Mitigation | SDG - 13 - Take urgent action to combat climate change and its impacts[b] | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this SDG. | New or improved knowledge/technology makes it possible to act
| IA - Environmental Health and Biodiversity | SDG - 12 - Ensure sustainable consumption and production patterns | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this SDG. | New or improved knowledge/technology makes it possible to act
| IA - Gender Equality, Youth and Social Inclusion | SDG - 5 - Achieve gender equality and empower all women and girls | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this SDG. | New or improved knowledge/technology makes it possible to act
| IA - Nutrition, Health and Food Security | SDG - 2 - End hunger, achieve food security and improved nutrition and promote sustainable agriculture | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this SDG. | New or improved knowledge/technology makes it possible to act
| IA - Poverty Reduction, Livelihoods and Jobs | SDG - 1 - End poverty in all its forms everywhere | As a result of the institutional innovations induced and scaled by this Initiative, new crop varieties are available and adopted by farmers, seed industry, food industry and consumers, contributing significantly to this SDG. | New or improved knowledge/technology makes it possible to act

## Research Questions
Work package | Output short title | Output statement | Research Question
Work Package 1 Market Intelligence |  |  | 2. Mapping future impact potentials to inform prioritization: What are the current and future global and regional impact challenges that can be converted into impact opportunities where CGIAR breeding programs are best placed (e.g., where are viable seed systems in place facilitating delivery of breeding products) to contribute to the five Impact Areas? Where are other Initiatives best placed?
Work Package 1 Market Intelligence |  |  | 4. Characterizing varietal demand: What are smallholders’ and consumers’ preferred varieties (by gender and social group) and how accessible are these in terms of price and availability?
Work Package 1 Market Intelligence |  |  | 3. Describing prioritized product market segments: Within prioritized market segments, what are current and future trait preferences (trait type and threshold of improvement) of farmers, agro-industry and consumers (by gender, social groups, income groups)?
Work Package 1 Market Intelligence | 1.0.1. High quality, relevant research is completed | High quality, relevant research is completed | 1. Building common framework: What concepts, methods, and tools are most suitable for the collection of market intelligence?
Work Package 2 Target Product Profile Design | 2.1.2 2.2.2.Gender-intentional target product profile | Gender-intentional target product profile | 2. Designing gender-intentional target product profiles and aligning them to market segments and breeding pipelines: What are the ideal products** for each market segment prioritized by WP1, and what changes are needed in breeding pipelines to ensure the ideal products are developed?
Work Package 2 Target Product Profile Design | 2.1.1. Standardize Protocol to develop gender-intentional target product profile design | Standardize Protocol to develop gender-intentional target product profile design | 1. Building the collaborative basis for target product profile design: What processes, structures, and frameworks are needed to facilitate productive engagement between stakeholders to develop inclusive target product profiles, especially the process of identifying and prioritizing the key traits to include in the target product profile?
Work Package 3 Behavioral Intelligence | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | 1. Providing behavioral intelligence for accelerating varietal turnover: What triggers women and men farmers and consumers to switch to a new variety or related product? What are the implications for strategies aimed at steering women and men farmers and consumers towards newer products? How cost-effective and equitable are these approaches? What are the trade-offs and synergies between Impact Areas?
Work Package 3 Behavioral Intelligence | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | 3. Synthesis and external validity: How do the findings from the experiments on accelerating varietal turnover and promoting new products vary across countries, product market segments and contexts? What drives this heterogeneity in cost-effectiveness and inclusivity (e.g., market structure, competition, policy environment, access to services)?
Work Package 3 Behavioral Intelligence | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | 2. Providing behavioral intelligence for promoting new products: What approaches and tools are most effective for private sector actors (e.g., seed businesses, processors, supermarkets) and NGOs to steer farmers and consumers towards newer products? What barriers and constraints prevent private sector actors and NGOs from implementing these approaches and tools? To what extent do these approaches and tools bring gender equality and inclusion and what are the trade-offs and synergies between Impact Areas?
Work Package 3 Behavioral Intelligence | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | 3. Synthesis and external validity: How do the findings from the experiments on accelerating varietal turnover and promoting new products vary across countries, product market segments and contexts? What drives this heterogeneity in cost-effectiveness and inclusivity (e.g., market structure, competition, policy environment, access to services)?
Work Package 4 Pipeline Investment Cases | 4.1.3., 4.2.3. Global Market Intelligence Platform (GloMIP) | Global Market Intelligence Platform (GloMIP) | 2. Supporting prioritization of breeding investments based on potential impact: Which pipelines have the greatest opportunity to contribute to the five Impact Areas in a given region, taking into account: market trends and marketing cost, farmer needs, gender gap elements, population growth, malnutrition epidemiology, and climate change? What are the trade-offs between Impact Areas and how do we compare and weigh them, e.g., between gender equality and productivity?
Work Package 4 Pipeline Investment Cases | 4.0.1. Novel applications of methods, metrics, and tools | Novel applications of methods, metrics, and tools | 1. What are the indicators for each Impact Area that are relevant for assessing the ex ante impact of breeding pipeline investments in CGIAR-NARES genetic innovation systems across the 5 Impact Areas and the 25 CGIAR crops? 2. What is the state of the art in measuring the indicators and assessing ex ante impacts of breeding pipeline investments in CGIAR-NARES genetic innovation systems across the 5 Impact Areas and the 25 CGIAR crops? 3. What methods, metrics and tools can be applied that make optimal use of the parameters defined in the existing Seed Product Market Segment (SPMS, WP1) and Target Product Profile (TPP, WP2) databases to assess the ex ante impact of breeding pipeline investments in CGIAR-NARES genetic innovation systems across the 5 Impact Areas and the 25 CGIAR crops, and what are the gaps in information and parameters that should be captured in the SPMS (WP1) and TPP (WP2) databases, and other (if applicable) databases?
Work Package 4 Pipeline Investment Cases | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | 2. Supporting prioritization of breeding investments based on potential impact: Which pipelines have the greatest opportunity to contribute to the five Impact Areas in a given region, taking into account: market trends and marketing cost, farmer needs, gender gap elements, population growth, malnutrition epidemiology, and climate change? What are the trade-offs between Impact Areas and how do we compare and weigh them, e.g., between gender equality and productivity?
Work Package 5 Institutional Scaling and MELIA | 5..1.2. Institutionalized innovations to facilitate and promote the use of market intelligence information | Institutionalized innovations to facilitate and promote the use of market intelligence information | 3. Outcomes: To what extent does the market intelligence generated through this Initiative change how breeding programs define product profiles, prioritize breeding targets, and allocate investments? And particularly, the rate at which new materials are developed?
Work Package 5 Institutional Scaling and MELIA | 5..1.2. Institutionalized innovations to facilitate and promote the use of market intelligence information | Institutionalized innovations to facilitate and promote the use of market intelligence information | 1. Institutional change: What are the key drivers and constraints (e.g., power relationships between social and biophysical scientists) and attitudes towards institutional change (adoption of institutional standards and processes developed in WP2) in product profile design in CGIAR-NARES-SME breeding networks?
Work Package 5 Institutional Scaling and MELIA | 5..1.2. Institutionalized innovations to facilitate and promote the use of market intelligence information | Institutionalized innovations to facilitate and promote the use of market intelligence information | 4. Impacts: How does institutional change in genetic innovation systems affect the total impact of breeding and seed systems and its distribution across the five CGIAR Impact Areas?
Work Package 5 Institutional Scaling and MELIA | 5..1.2. Institutionalized innovations to facilitate and promote the use of market intelligence information | Institutionalized innovations to facilitate and promote the use of market intelligence information | 2. Scaling: Which scaling mechanisms can successfully promote institutional change? What is the comparative effectiveness of the new market intelligence-informed breeding and seed systems approach as compared to existing approaches?
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | 3. Outcomes: To what extent does the market intelligence generated through this Initiative change how breeding programs define product profiles, prioritize breeding targets, and allocate investments? And particularly, the rate at which new materials are developed?
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | 4. Impacts: How does institutional change in genetic innovation systems affect the total impact of breeding and seed systems and its distribution across the five CGIAR Impact Areas?
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | 1. Institutional change: What are the key drivers and constraints (e.g., power relationships between social and biophysical scientists) and attitudes towards institutional change (adoption of institutional standards and processes developed in WP2) in product profile design in CGIAR-NARES-SME breeding networks?
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | 2. Scaling: Which scaling mechanisms can successfully promote institutional change? What is the comparative effectiveness of the new market intelligence-informed breeding and seed systems approach as compared to existing approaches?

## Scientific Methods
Work Package | Output short title | Output statement | Scientific Method
Work Package 1 Market Intelligence |  |  | Crop modeling featuring IPCC AR6 climate projections in target population environments
Work Package 1 Market Intelligence |  |  | Joint strategic foresight analysis with Foresight and Metrics to anticipate a range of possible future scenarios and impact potentials (Glover et al, 2021; Miller and Poli, 2010), in collaboration with other Initiatives: Plant Health, HER+, SHiFT, FRESH, ClimBeR, and EiA. This will include analysis of trade-offs and synergies across future impact potentials
Work Package 1 Market Intelligence |  |  | Demand analysis for Precision Genetic Technologies to anticipate acceptability in sub-national markets, export, organic and traditional markets, as well as impact on gender
Work Package 1 Market Intelligence |  |  | Review of secondary data, expert consultations, key informant interviews, spatial analysis
Work Package 1 Market Intelligence |  |  | Rapid survey techniques, field experiments, experimental auctions, participatory tools/games to assess gender disaggregated trait preferences, trade-offs among them, and demand for improved varieties, supported by genotype-based varietal monitoring data from Seed Equal and IMAGE
Work Package 1 Market Intelligence |  |  | Farmer/consumer surveys, GIS and spatial analysis tools, key informant interviews, participatory techniques, choice experiments, gender analysis and secondary information
Work Package 1 Market Intelligence |  |  | Participatory workshops with breeders, seed companies, NARES, CGIAR breeding teams, and food industry representatives
Work Package 1 Market Intelligence |  |  | Evaluation of psychological drivers of key stakeholders: perceptions, attitudes and beliefs, motivation, and learning
Work Package 1 Market Intelligence |  |  | Joint research with SHiFT, Excellence in Agronomy, and Plant Health Initiatives, to inform crop/trait priorities
Work Package 1 Market Intelligence | 1.0.1. High quality, relevant research is completed | High quality, relevant research is completed | Transdisciplinary tool design working group
Work Package 1 Market Intelligence | 1.0.1. High quality, relevant research is completed | High quality, relevant research is completed | Literature review of published work by CGIAR, NARES, universities, NGOs, and others, covering existing concepts, methods and tools
Work Package 2 Target Product Profile Design |  |  | Review national seed variety registration trial protocols to verify whether market segments are categories in the testing program; if not, transdisciplinary team develops proposal to run variety registration trial for each market segment
Work Package 2 Target Product Profile Design | 2.1.2 2.2.2.Gender-intentional target product profile | Gender-intentional target product profile | Regional transdisciplinary* CGIAR-NARES-SME team building and consensus building workshops to balance heterogeneous interests and opinions
Work Package 2 Target Product Profile Design | 2.1.2 2.2.2.Gender-intentional target product profile | Gender-intentional target product profile | Analysis of trade-offs and synergies across traits that target different Impact Areas
Work Package 2 Target Product Profile Design | 2.1.2 2.2.2.Gender-intentional target product profile | Gender-intentional target product profile | Review of the scales currently used to score traits across crops and to develop a recommendation to harmonize scales for traits across crops (e.g., Custodio et al., 2019)
Work Package 2 Target Product Profile Design | 2.1.2 2.2.2.Gender-intentional target product profile | Gender-intentional target product profile | Formation of expert panels of individuals with experience and understanding in key areas to determine translation of key characteristics (e.g., nutritional, sensory and biophysical characteristics such as taste, mouthfeel, texture) to measurable traits (e.g., Aznan et al., 2021)
Work Package 2 Target Product Profile Design | 2.1.2 2.2.2.Gender-intentional target product profile | Gender-intentional target product profile | Transdisciplinary regional teams translate market intelligence from WP1 into gender-intentional target product profiles. WP2 coordinates with Accelerated Breeding WP1 to determine the size and structure of breeding pipelines, the number of market segments a breeding pipeline focuses on, assigning a tier of breeding effort to each market segment and using a stage gate advancement process based on the gender-intentional target product profile for each market segment. Target product profiles for Precision Genetic Technologies will also be aligned with gender-intentional target product profile
Work Package 2 Target Product Profile Design | 2.1.2 2.2.2.Gender-intentional target product profile | Gender-intentional target product profile | Expert elicitation, collective induction, group consensus building
Work Package 2 Target Product Profile Design | 2.1.1. Standardize Protocol to develop gender-intentional target product profile design | Standardize Protocol to develop gender-intentional target product profile design | Development of quantitative and qualitative indicators to assess transdisciplinary practice and empowerment through social network analysis: diversity of participants, whether and how integration and collaboration are occurring, the relative degrees of network stability and fragility and how the network is structured to achieve its goals (Steelman et al., 2021)
Work Package 2 Target Product Profile Design | 2.1.1. Standardize Protocol to develop gender-intentional target product profile design | Standardize Protocol to develop gender-intentional target product profile design | Expert elicitation, collective induction, group consensus building
Work Package 2 Target Product Profile Design | 2.1.1. Standardize Protocol to develop gender-intentional target product profile design | Standardize Protocol to develop gender-intentional target product profile design | Transdisciplinary regional teams translate market intelligence from WP1 into gender-intentional target product profiles. WP2 coordinates with Accelerated Breeding WP1 to determine the size and structure of breeding pipelines, the number of market segments a breeding pipeline focuses on, assigning a tier of breeding effort to each market segment and using a stage gate advancement process based on the gender-intentional target product profile for each market segment. Target product profiles for Precision Genetic Technologies will also be aligned with gender-intentional target product profile
Work Package 2 Target Product Profile Design | 2.1.1. Standardize Protocol to develop gender-intentional target product profile design | Standardize Protocol to develop gender-intentional target product profile design | Regional transdisciplinary* CGIAR-NARES-SME team building and consensus building workshops to balance heterogeneous interests and opinions
Work Package 2 Target Product Profile Design | 2.1.1. Standardize Protocol to develop gender-intentional target product profile design | Standardize Protocol to develop gender-intentional target product profile design | Formation of expert panels of individuals with experience and understanding in key areas to determine translation of key characteristics (e.g., nutritional, sensory and biophysical characteristics such as taste, mouthfeel, texture) to measurable traits (e.g., Aznan et al., 2021)
Work Package 3 Behavioral Intelligence |  |  | Close collaboration with Seed Equal and IMAGE to identify factors of adoption and disadoption of improved varieties
Work Package 3 Behavioral Intelligence | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | Qualitative work (e.g., in-depth interviews, ethnographic observations, focus group discussions, key informant interviews, semi-structured interviews) will help understand how the strategies employed in the experiments do (not) influence behavior.
Work Package 3 Behavioral Intelligence | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | Field experiments with alternative approaches to encourage private sector actors to start marketing new gender responsive varieties and related products at an accelerated rate.
Work Package 3 Behavioral Intelligence | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | Field experiments, randomized trials and A/B testing of various strategies
Work Package 3 Behavioral Intelligence | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | Meta-analysis or synthesis research linking differences in cost-effectiveness and inclusivity from experiments under research questions 1 and 2 to characteristics of farmers, consumers and the decision-making environment that differ across experiments, complemented by rigorous qualitative research
Work Package 3 Behavioral Intelligence | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | Qualitative interviews with private sector actors and NGOs aimed at understanding their business models and the risks and barriers that prevent them from promoting new varieties and products, and insights on how to overcome these barriers
Work Package 3 Behavioral Intelligence | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | Experimental methods will be used to estimate causal effects of alternative approaches, such as vouchers, other types of incentives, information, delivery methods, trial packs/products, and behavioral nudges.
Work Package 3 Behavioral Intelligence | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | Meta-analysis or synthesis research linking differences in cost-effectiveness and inclusivity from experiments under research questions 1 and 2 to characteristics of farmers, consumers and the decision-making environment that differ across experiments, complemented by rigorous qualitative research
Work Package 3 Behavioral Intelligence | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | Qualitative work (e.g., in-depth interviews, ethnographic observations, focus group discussions, key informant interviews, semi-structured interviews) will help understand how the strategies employed in the experiments do (not) influence behavior.
Work Package 3 Behavioral Intelligence | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | Field experiments with alternative approaches to encourage private sector actors to start marketing new gender responsive varieties and related products at an accelerated rate.
Work Package 3 Behavioral Intelligence | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | Field experiments, randomized trials and A/B testing of various strategies
Work Package 3 Behavioral Intelligence | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | Qualitative interviews with private sector actors and NGOs aimed at understanding their business models and the risks and barriers that prevent them from promoting new varieties and products, and insights on how to overcome these barriers
Work Package 3 Behavioral Intelligence | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | Experimental methods will be used to estimate causal effects of alternative approaches, such as vouchers, other types of incentives, information, delivery methods, trial packs/products, and behavioral nudges.
Work Package 4 Pipeline Investment Cases |  |  | Investment and cost analysis, in collaboration with Breeding Resources
Work Package 4 Pipeline Investment Cases | 4.1.3., 4.2.3. Global Market Intelligence Platform (GloMIP) | Global Market Intelligence Platform (GloMIP) | Portfolio analysis
Work Package 4 Pipeline Investment Cases | 4.1.3., 4.2.3. Global Market Intelligence Platform (GloMIP) | Global Market Intelligence Platform (GloMIP) | Develop approaches to determine potential benefits and incorporate risk preferences within targeted market segments.
Work Package 4 Pipeline Investment Cases | 4.1.3., 4.2.3. Global Market Intelligence Platform (GloMIP) | Global Market Intelligence Platform (GloMIP) | Develop approaches to build scenarios of combinations of pipelines and levels of investment and compare the impact of each scenario against the Impact Areas.
Work Package 4 Pipeline Investment Cases | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | Explore options to align data provided by WP1 on market segments from ABI WP1 on the alignment of pipelines to market segments to estimate the contribution of each pipeline to the five CGIAR Impact Areas.
Work Package 4 Pipeline Investment Cases | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | Close collaboration with Seed Equal and IMAGE to incorporate varietal adoption and turnover data into ROI analysis
Work Package 4 Pipeline Investment Cases | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | Benefit-cost analysis
Work Package 4 Pipeline Investment Cases | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | Return on Investment (ROI) analysis, disaggregated by crops, regions, gender, social groups, income groups, and Impact Areas
Work Package 4 Pipeline Investment Cases | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | Use outputs from WP3 to determine the potential varietal turnover and costs of marketing the varieties from a given pipeline.
Work Package 4 Pipeline Investment Cases | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | Ex-ante impact assessment
Work Package 4 Pipeline Investment Cases | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | Bio-economic modeling
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Review of literature on institutional change and management
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Surveys including focus group discussions, and key informant interviews; data analyzed through multi-stage adoption models to identify key drivers and constraints of institutional adoption (e.g., Lenaerts et al., 2021)
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Meta-analysis (e.g., Lenaerts et al., 2018)
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative and quantitative approaches to understanding, tracking and documenting institutional change among system actors
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Ex-post impact evaluation using (quasi-)experimental methods to identify impacts of varieties from past breeding efforts that have targeted socio-economic or gender-relevant crop variety traits relative to breeding efforts that have mainly focused on biophysical traits (e.g., yields, nutrient density, or stress tolerance)
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Analysis of impact trade-offs and synergies across Impact Areas and SDGs (e.g., Hegre et al., 2020)
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Role-playing games to facilitate social learning and collective action towards institutional change (e.g., Salvini et al., 2016)
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Innovation Packages and Scaling Readiness approach to characterize the level of scaling readiness of the four Core Innovations: (i) Institutional Innovation; (ii) G×I Learning Alliance; (iii) Global Market Intelligence Platform; and (iv) Investor Dashboard (see Section 4).
Work Package 5 Institutional Scaling and MELIA | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Testing and validating scaling approaches (old/new) of institutional change in different contexts using both experimental and quasi-experimental approaches

## Result Framework
WP Title | Result type (outcome or output) | Result Short title | Result Statement | Result Type | Responsible Organization | Partners | Outcome actor type | Outcome actor type of change | Outcome: Is actor a partner? | Qualitative: minimum level of success | Qualitative: moderate level of success | Qualitative: maximum level of success | Location | Country | Region | Indicator | Type | Unit of measurement | Data source | Data collection method | Data collection frequency | Location | Country | Region | Baseline value | Baseline date | Target value | Target date
Work Package 1 Market Intelligence | OUTPUT | 1.0.1. High quality, relevant research is completed | High quality, relevant research is completed | Innovation | International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo | International Potato Center, International Rice Research Institute, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Institute of Tropical Agriculture, Africa Rice Center | [9 empty] | Number of knowledge products | Number of knowledge products | Report | Primary data | Expert consultation | Once | global |  |  | 0 | 30/06/2022 | 2 4 | 31/12/2023 31/12/2024
Work Package 1 Market Intelligence | OUTPUT | 1.0.2. Evidence-informed discussions facilitated | Evidence-informed discussions facilitated | Capacity | International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo | Africa Rice Center, International Institute of Tropical Agriculture, International Rice Research Institute, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Potato Center | [9 empty] | Number of activities | Number of activities | Number | Primary data | Expert consultation | Once | global |  |  | 0 | 30/06/2022 | 25 50 | 31/12/2023 31/12/2024
Work Package 2 Target Product Profile Design | OUTCOME | 2.1. CGIAR and National partners institutionalize transdisciplinary teams to systematically co-design target product profiles | 2.1. CGIAR and National partners institutionalize transdisciplinary teams to systematically co-design target product profiles | Capacity | International Institute of Tropical Agriculture | International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, International Rice Research Institute, International Food Policy Research Institute, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), Africa Rice Center, International Livestock Research Institute, International Potato Center, International Center for Agricultural Research in the Dry Areas |  |  | Yes |  |  |  | regional |  | Sub-Saharan Africa, Latin America and the Caribbean, South-Eastern Asia, Southern Asia | Proportion of TPPs that were designed by transdisciplinary teams​ (% TPPs designed by transdisciplinary teams) |  | Percent | Primary data collected through Initiative | Administrative user data | Semi - Annual | global |  |  | 0 | 30/06/2022 | 50 70 | 31/12/2023 31/12/2024
Work Package 2 Target Product Profile Design | OUTPUT | 2.1.1. Standardize Protocol to develop gender-intentional target product profile design | Standardize Protocol to develop gender-intentional target product profile design | Innovation | International Institute of Tropical Agriculture | Africa Rice Center, International Rice Research Institute, International Potato Center, International Center for Agricultural Research in the Dry Areas, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, International Livestock Research Institute, International Food Policy Research Institute | [9 empty] | Number of manuals developed | Number of manuals developed | Number | Scientists mapped in the initiative, and other disciplines to support in coming up with the standards | Expert consultation | Once | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2024
Work Package 2 Target Product Profile Design | OUTPUT | 2.1.2 2.2.2.Gender-intentional target product profile | Gender-intentional target product profile | Innovation | International Institute of Tropical Agriculture | Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Rice Research Institute, International Potato Center, International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, International Center for Agricultural Research in the Dry Areas, Africa Rice Center, International Livestock Research Institute | [9 empty] | Number of target product profiles (disaggregated by gender and market segment) | Number of target product profiles (disaggregated by gender and market segment) | Number | Scientists mapped in the initiative, and other disciplines to support in coming up with the standards | Expert consultation | Annual | global |  |  | 0 | 30/06/2022 | 297 111 | 31/12/2023 31/12/2024
Work Package 2 Target Product Profile Design | OUTCOME | 2.2. CGIAR and National partners breeding programs use Target Product Profiles (TPP's) for breeding decisions | 2.2. CGIAR and National partners breeding programs use Target Product Profiles (TPP's) for breeding decisions Advancement Meetings | Uptake of information product | International Institute of Tropical Agriculture | International Center for Agricultural Research in the Dry Areas, International Rice Research Institute, International Potato Center, Africa Rice Center, International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Livestock Research Institute |  |  | Yes |  |  |  | global |  |  | Percentage of CGIAR breeding pipelines using target product profiles for the market segments they are breeding for (% of breeding pipelines using TTPs) |  | Percent | Institutional adoption study | Surveys with breeders and other CGIAR and partner decision-makers on actual adoption and willingness to adopt | Annual | global |  |  | 0 | 30/06/2022 | 50 60 | 31/12/2023 31/12/2024
Work Package 3 Behavioral Intelligence | OUTCOME | 3.1. Seed systems actors share behavioral intelligence on how to accelerate varietal turnover with others in their institutions | Seed systems actors share behavioral intelligence on how to accelerate varietal turnover with others in their institutions | Uptake of information product | International Food Policy Research Institute | International Institute of Tropical Agriculture, International Potato Center, International Rice Research Institute |  |  | Yes |  |  |  | global |  |  | Number of organizations sharing behavioral intelligence |  | Number | Primary data collected through Initiative | Surveys with CGIAR and partner decision-makers |  | global |  |  | 0 | 31/12/2023 | 1 | 31/12/2024
Work Package 3 Behavioral Intelligence | OUTPUT | 3.1.1. Behavioural intelligence for accelerating varietal turnover | Behavioural intelligence for accelerating varietal turnover | Information product | International Food Policy Research Institute | International Rice Research Institute, International Institute of Tropical Agriculture, International Potato Center | [9 empty] | Number of knowledge products (disaggregated by report; working paper, protocol) | Number of knowledge products (disaggregated by report; working paper, protocol) | Number | Primary and secondary data collected through Initiative | Randomized controlled trials and qualitative interviews​ |  | global |  |  | 0 | 31/12/2022 | 8 3 | 31/12/2023 31/12/2024
Work Package 3 Behavioral Intelligence | OUTPUT | 3.1.3., 3.2.3., 3.3.3. Global Behavioral intelligence based on meta-analysis and synthesis | Global Behavioral intelligence based on meta-analysis and synthesis | Information product | International Food Policy Research Institute | International Institute of Tropical Agriculture, International Rice Research Institute, International Potato Center | [9 empty] | Number of knowledge products developed (disaggregated by;briefs) | Number of knowledge products developed (disaggregated by;briefs) | Number | Primary and secondary data collected through Initiative | Randomized controlled trials |  | global |  |  | 0 | 30/06/2022 | 1 2 | 31/12/2023 31/12/2024
Work Package 3 Behavioral Intelligence | OUTPUT | 3.2.2. Behavioural intelligence for promoting new products | Behavioural intelligence for promoting new products | Information product | International Food Policy Research Institute | International Rice Research Institute, International Potato Center, International Institute of Tropical Agriculture | [9 empty] | Number of knowledge products (dis.by by type;blogs; slide decks) | Number of knowledge products (dis.by by type;blogs; slide decks) | Number | Primary data collected through Initiative | Qualitative interviews, case studies |  | global |  |  | 0 | 30/06/2022 | 6 6 | 31/12/2023 31/12/2024
Work Package 3 Behavioral Intelligence | OUTCOME | 3.2.Private sector and NGOs co-design strategies to address supply-side constraints to promoting new varieties and related products | Private sector and NGOs co-design strategies to address supply-side constraints to promoting new varieties and related products | Uptake of information product | International Food Policy Research Institute | International Potato Center, International Institute of Tropical Agriculture, International Rice Research Institute |  |  | Yes |  |  |  | global |  |  | Number of strategies developed | Number of policies/ strategies/ laws/ regulations/ budgets/ investments/ curricula modified in design or implementation, informed by CGIAR research. | Number | Case studies with industry and NGOs | Qualitative and quantitative surveys on whether intelligence from Initiative is used | Annual | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2024
Work Package 3 Behavioral Intelligence | OUTCOME | 3.3. CGIAR and partners design research projects of high quality leading to rigorous behavioural intelligence | CGIAR and partners design research projects of high quality leading to rigorous behavioural intelligence | Uptake of information product |  |  | research institution | change in behavior/practice | Yes |  |  |  | global |  |  | Number of research project proposal developed |  | Number | Case studies with industry and NGOs | Qualitative and quantitative surveys on whether intelligence from Initiative is used |  | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2024
Work Package 4 Pipeline Investment Cases | OUTPUT | 4.0.1. Novel applications of methods, metrics, and tools | Novel applications of methods, metrics, and tools | Information product | International Rice Research Institute | HarvestPlus, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), Africa Rice Center, International Potato Center, International Food Policy Research Institute | [9 empty] | Number of knowledge products developed (disaggregated by type) | Number of knowledge products developed (disaggregated by type) | Number | Primary and secondary data | Systematic analysis | Annual | global |  |  | 0 | 30/06/2022 | 3 4 | 31/12/2023 31/12/2024
Work Package 4 Pipeline Investment Cases | OUTCOME | 4.1. CGIAR-NARES-SME breeding networks implement breeding pipelines that are aligned to the five Impact Areas | CGIAR-NARES-SME breeding networks implement breeding pipelines that are aligned to the five Impact Areas | Uptake of information product | International Rice Research Institute | International Potato Center, International Center for Agricultural Research in the Dry Areas, International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, Africa Rice Center, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Food Policy Research Institute, International Institute of Tropical Agriculture |  |  | Yes |  |  |  | global |  |  | Percentage of impact opportunities captured by breeding pipelines as measured by priority index in GloMIP |  | Percent | Institutional adoption study | Surveys with breeders and other CGIAR and partner decision-makers | Annual | global |  |  | 0 | 01/01/2022 | 30 | 31/12/2024
Work Package 4 Pipeline Investment Cases | OUTPUT | 4.1.2., 4.2.2. Pipeline investment cases | Pipeline investment cases | Innovation | International Rice Research Institute | International Potato Center, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), HarvestPlus | [9 empty] | Number of knowledge products developed (disaggregated by type) | Number of knowledge products developed (disaggregated by type) | Number | Primary and secondary data | Systematic analysis | Semi-Annual | global |  |  | 0 | 30/06/2022 | 2 4 | 31/12/2023 31/12/2024
Work Package 4 Pipeline Investment Cases | OUTPUT | 4.1.3., 4.2.3. Global Market Intelligence Platform (GloMIP) | Global Market Intelligence Platform (GloMIP) | Information product | International Rice Research Institute | Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Institute of Tropical Agriculture, International Food Policy Research Institute, International Potato Center, International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo | [9 empty] | Number of online data portal | Number of online data portal | Number | Primary and secondary | Systematic curation and visualization | Once | global |  |  | 0 | 30/06/2022 | 1 1 | 31/12/2023 31/12/2024
Work Package 4 Pipeline Investment Cases | OUTPUT | 4.2.4 Investor Dashboard (hosted in GloMIP) | Investor Dashboard (hosted in GloMIP) | Capacity | [11 empty] | # of tools (disaggregated by platform; dashboard) | # of tools (disaggregated by platform; dashboard) | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2024
Work Package 4 Pipeline Investment Cases | OUTCOME | 4.2.CGIAR breeders use GloMIP and the Investor Dashboard to align breeding pipeline investment efforts commensurate to Impact Opportunities, Projected Benefits, and Returns on Investment across the five Impact Areas | CGIAR breeders use GloMIP and the Investor Dashboard to align breeding pipeline investment efforts commensurate to Impact Opportunities, Projected Benefits, and Returns on Investment across the five Impact Areas | Uptake of information product | International Rice Research Institute | International Center for Agricultural Research in the Dry Areas, International Institute of Tropical Agriculture, International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, Africa Rice Center, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Food Policy Research Institute, International Potato Center |  |  | Yes |  |  |  | global |  |  | Number of organisations whose breeding budget (from CGIAR) was allocated based on the GloMIP Impact Opportunities Portal |  | Number | Primary data | Surveys with research leaders and investors | Annual | global |  |  | 0 | 01/01/2022 | 8 | 31/12/2024
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5..1.2. Institutionalized innovations to facilitate and promote the use of market intelligence information | Institutionalized innovations to facilitate and promote the use of market intelligence information | Capacity | International Potato Center | [10 empty] | Number of baseline studies | Number of baseline studies | Number | Primary data collected through Initiative | Surveys, key informant interviews and participant observation | Annual | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2024
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5..1.2. Institutionalized innovations to facilitate and promote the use of market intelligence information | Institutionalized innovations to facilitate and promote the use of market intelligence information | Capacity | International Potato Center | [10 empty] | Number of ethical approvals | Number of ethical approvals | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2023
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5..1.2. Institutionalized innovations to facilitate and promote the use of market intelligence information | Institutionalized innovations to facilitate and promote the use of market intelligence information | Capacity | International Potato Center | [10 empty] | Number of baseline tools designed | Number of baseline tools designed | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2023
Work Package 5 Institutional Scaling and MELIA | OUTCOME | 5.1 CGIAR-NARES-SME breeding networks’ knowledge enhanced on the contribution of institutional change in genetic innovation to the five impact areas | CGIAR-NARES-SME breeding networks’ knowledge enhanced on the contribution of institutional change in genetic innovation to the five impact areas | Capacity |  |  |  |  | Yes |  |  |  | global |  |  | Number of network members engaged in knowledge generation on the contribution of institutional change to the five Impact Areas |  | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 20 | 31/12/2024
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Capacity | International Potato Center | [10 empty] | Capacity development plan | NA | Cap dev plan | Primary data collected through Initiative | Focus Groups discussion and key informant interviews | Annual | global |  |  |  |  | 1 | 31/12/2023
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Capacity | International Potato Center | [10 empty] | Identification of Target (pilot) networks | NA | networks | Primary data collected through Initiative | Surveys and interviews with users | Annual | global |  |  |  |  | 3 | 31/12/2023
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Capacity | International Potato Center | [10 empty] | Framework and SOP for partner engagement | NA | SOP report | Primary data collected through Initiative | Focus Groups discussion and key informant interviews | Annual | global |  |  |  |  | 1 report | 31/12/2023
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.1. Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Qualitative/quantitative baseline investigations of the behavioral adaptation and institutional incentives | Capacity | International Potato Center | [10 empty] | Diagnostic study of entry points for partner institutions. | NA | Diagnostic study report​ | Primary data collected through Initiative | Surveys and interviews with users | Annual | global |  |  |  |  | 1 study | 31/12/2023
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.3. Institutional Innovations design advanced | Institutional Innovations design advanced | Innovation | International Potato Center | [10 empty] | Number of knowledge products developed (disaggregated by type) | Number of knowledge products developed (disaggregated by type) | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2024
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.4. Address gender intentionality in breeding decision making | Address gender intentionality in breeding decision making | Information product | International Potato Center | [10 empty] | Number of knowledge products developed (disaggregated by type) | Number of knowledge products developed (disaggregated by type) | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 5 4 | 31/12/2023 31/12/2024
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.5. Study to understand how MI influences investment in breeding pipelines | Study to understand how MI influences investment in breeding pipelines | Information product | International Potato Center | [10 empty] | Number of knowledge products developed (disaggregated by type: study) | Number of knowledge products developed (disaggregated by type: study) | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 1 1 | 31/12/2023 31/12/2024
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.6. Study on the potential impact of different degrees of market smart varieties (across the 5 impact areas) | Study on the potential impact of different degrees of market smart varieties (across the 5 impact areas) | Information product | International Potato Center | [10 empty] | Number of knowledge products developed (disaggregated by type: study) | Number of knowledge products developed (disaggregated by type: study) | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 1 | 31/12/2024
Work Package 5 Institutional Scaling and MELIA | OUTPUT | 5.1.7. Adaptive planning | Adaptive planning | Capacity | International Potato Center | [10 empty] | Number of knowledge products developed (disaggregated by type) | Number of knowledge products developed (disaggregated by type) | Number |  |  |  | global |  |  | 0 | 30/06/2022 | 2 2 | 31/12/2023 31/12/2024

## EOI-O
EOI-O title | EOI-O Statement | Outcome Type | Responsible Organization | Partners | Actor type | Actor type of change | Is actor a partner? | Qualitative: minimum level of success | Qualitative: moderate level of success | Qualitative: maximum level of success | Location | Country | Region | Indicator | Type | Unit of measurement | Data source | Data collection method | Data collection frequency | Location | Country | Region | Baseline value | Baseline date | Target value | Target date
1. CGIAR and national partners share institutional standards & market and behavioral intelligence | CGIAR and national partners share institutional standards & market and behavioral intelligence | uptake of information product | International Rice Research Institute | International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, International Institute of Tropical Agriculture, Africa Rice Center, International Center for Agricultural Research in the Dry Areas, International Potato Center, International Food Policy Research Institute, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical) | research institution | change in behavior/practice | Yes |  |  |  | regional |  | South-Eastern Asia, Southern Asia, Latin America and the Caribbean, Sub-Saharan Africa | Number of standards and intelligence disseminated |  | Number | Institutional adoption study | Surveys with breeders and other CGIAR and partner decision-makers on actual adoption and willingness to adopt | Annual | global |  |  | 0 | 01/01/2022 | 4 | 31/12/2024
2. Research leaders and investors make investment decisions in genetic innovation using GloMIP and the Investor Dashboard | Research leaders and investors make investment decisions in genetic innovation using GloMIP and the Investor Dashboard | uptake of information product | International Rice Research Institute | Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Center for Agricultural Research in the Dry Areas, International Institute of Tropical Agriculture, Africa Rice Center, International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, International Potato Center, International Food Policy Research Institute | research institution | change in behavior/practice | Yes |  |  |  | global |  |  | Number of pipeline investment cases (based on GloMIP and the Investor Dashboard) being taken up research leaders and investors |  | Number | Investor Dashboard; Primary data | Tracking/usage data collected by server/host of Dashboard ; Qualitative and quantitative interviews with next users on (intention to be) using outputs from Initiative to guide investments | Annual | global |  |  | 0 | 01/01/2022 | 3 | 31/12/2024
3. Seed industry and NGOs use market and behavioral intelligence | Seed industry and NGOs use market and behavioral intelligence | uptake of information product | International Rice Research Institute | International Institute of Tropical Agriculture, International Food Policy Research Institute, International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, International Potato Center, Africa Rice Center, International Center for Agricultural Research in the Dry Areas, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical) |  | change in behavior/practice | Yes |  |  |  | global |  |  | Number of organizations using market and behavioral intelligence | Number of organizations using market and behavioral intelligence | Number | Case studies with industry and NGOs | Qualitative and quantitative surveys on how market and behavioral intelligence from initiative informs strategies | Annual | global |  |  | 0 | 01/01/2022 | 3 | 31/12/2024
4. Transdisciplinary teams across CGIAR and partners co-implement market and behavioral intelligence and co-design of target product profiles | Transdisciplinary teams across CGIAR and partners co-implement market and behavioral intelligence and co-design of target product profiles | capacity | International Rice Research Institute | International Potato Center, International Maize and Wheat Improvement Center / Centro Internacional de Mejoramiento de Maíz y Trigo, Africa Rice Center, International Institute of Tropical Agriculture, Alliance of Bioversity and CIAT - Regional Hub (International Center for Tropical Agriculture / Centro Internacional de Agricultura Tropical), International Center for Agricultural Research in the Dry Areas, International Food Policy Research Institute | research institution | change in skills | Yes |  |  |  | regional |  | Latin America and the Caribbean, Sub-Saharan Africa, South-Eastern Asia, Southern Asia | Number of Transdisciplinary teams empowered | Change in the capacity of key (a) Individuals, (b) Organizations (government, civil society and private sector), and (c) Networks (e.g. multi-stakeholder platforms). | Number | Primary data | Administrative user data | Semi-Annual | global |  |  | 0 | 01/01/2022 | 3 | 31/12/2024

## AA-O
Action Area | Outcome | Indicator | Description
Genetic Innovation | CGIAR partners develop and scale innovations that contribute to the empowerment of women and other social groups in food, land, and water systems. | GIi 4.1 - Proportion of CGIAR-NARS-SME networks that have developed systems to measure adoption of innovations with gender implications (with sex and age disaggregation, using innovative and lower cost systems).
Genetic Innovation | CGIAR-NARS-SME networks use market segments, target product profiles to orient variety development and deployment towards those that provide larger scale benefits across the 5 Impact Areas. | RAFSi 3.1 - Proportion of CGIAR-NARS-SME breeding pipelines within CGIAR-NARS-SME network using market segments, target product profiles to guide selection decisions for all advancement steps.
Genetic Innovation | Integrated seed systems increase the quantity of quality seed of improved varieties available to farmers for priority crops and in selected countries, geographies, and market segments

## IA
IA | Global Target | Indicator | Description
Climate Adaptation and Mitigation | Equip 500 million small-scale producers to be more resilient to climate shocks, with climate adaptation solutions available through national innovation systems. | #people benefiting from climate-adapted innovations, #tonnes CO2 equivalent emissions, #$ climate adaptation investments, #people benefiting from the implementation of adaptation plans, #plans with evidence of implementation | Equip 500 million small-scale producers to be more resilient to climate shocks, with climate adaptation solutions available through national innovation systems
Environmental Health and Biodiversity | Stay within planetary and regional environmental boundaries: consumptive water use in food production of less than 2500 km3 per year (with a focus on the most stressed basins), zero net deforestation, nitrogen application of 90 Tg per year (with a redistribution towards low-input farming system) and increased use efficiency; and phosphorus application of 10 Tg per year. | #plant genetic accessions available and safely duplicated, #ha deforestation, #Tg nitrogen application, #km3 consumptive water use, #ha under improved management | Stay within planetary and regional environmental boundaries consumptive water use in food production of less than 2500 km3 per year (with a focus on the most stressed basins), zero net deforestation nitrogen application of 90Tg per year (with a redistribution towards low-input farming system) and increased use efficiency and phosphorus application of 10Tg per year
Gender Equality, Youth and Social Inclusion | Close the gender gap in rights to economic resources, access to ownership and control over land and natural resources for over 500 million women who work in food, land and water systems. | #women assisted to exit poverty, #women’s empowerment and inclusion in the agricultural sector, #women benefiting from relevant CGIAR innovations, #youth benefiting fromrelevant CGIAR innovations | Close the gender gap in rights to economic resources, access to ownership and control over land and natural resources for over 500 million women who work in food, land and water systems
Nutrition, Health and Food Security | End hunger for all and enable affordable healthy diets for the 3 billion people who do not currently have access to safe and nutritious food. | #people meeting minimum micronutrient requirements, #people meeting minimum dietary energy requirements | End hunger for all and enable affordable healthy diets for the 3 billion people who do not currently have access to safe and nutritious food
Poverty Reduction, Livelihoods and Jobs | Reduce by at least half the proportion of men, women and children of all ages living in poverty in all its dimensions according to national definitions. | #poor people benefiting from relevant CGIAR innovations, #people assisted to exit poverty | Reduce by at least half the proportion of men, women, and children of all ages living in poverty in all its dimensions according to national definitions

## SDG
SDG | Target | Description
1 - End poverty in all its forms everywhere | 1.2 By 2030, reduce at least by half the proportion of men, women and children of all ages living in poverty in all its dimensions according to national definitions, 1.1 By 2030, eradicate extreme poverty for all people everywhere, currently measured as people living on less than $1.25 a day
2 - End hunger, achieve food security and improved nutrition and promote sustainable agriculture | 2.4 By 2030, ensure sustainable food production systems and implement resilient agricultural practices that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality, 2.1 By 2030, end hunger and ensure access by all people, in particular the poor and people in vulnerable situations, including infants, to safe, nutritious and sufficient food all year round, 2.3 By 2030, double the agricultural productivity and incomes of small-scale food producers, in particular women, indigenous peoples, family farmers, pastoralists and fishers, including through secure and equal access to land, other productive resources and inputs, knowledge, financial services, markets and opportunities for value addition and non-farm employment, 2.2 By 2030, end all forms of malnutrition, including achieving, by 2025, the internationally agreed targets on stunting and wasting in children under 5 years of age, and address the nutritional needs of adolescent girls, pregnant and lactating women and older persons
5 - Achieve gender equality and empower all women and girls | 5.a Undertake reforms to give women equal rights to economic resources, as well as access to ownership and control over land and other forms of property, financial services, inheritance and natural resources, in accordance with national laws
12 - Ensure sustainable consumption and production patterns | 12.a Support developing countries to strengthen their scientific and technological capacity to move towards more sustainable patterns of consumption and production
13 - Take urgent action to combat climate change and its impacts[b] | 13.1 Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries

## Other initiatives
Work Package | Other initiative name | Other initiative Work package name
Accelerating Crop Improvement Through Genome Editiong (GEdI)
Work Package 1 Bridging Knowledge Gaps and Networks: Plant Health Threat Identification and Characterization | Plant Health and Rapid Response to Protect Food Security and Livelihoods
Work Package 1 Consumers and their food environments | Sustainable Healthy Diets through Food Systems Transformation
Work Package 1 Megatrends affecting food, land, and water systems at global and regional scales (WP1) | Foresight and Metrics to Accelerate Food, Land, and Water Systems Transformation
Work Package 1 STRATEGIC MODERNISATION | Breeding Resources
Work Package 1 Understanding and influencing consumer behavior | Fruit and Vegetables for Sustainable Healthy Diets
Work Package 5 Platforms & Services | Harnessing Digital Technologies for Timely Decision-Making across Food, Land, and Water Systems
Work Package 5 Policies for varietal turnover, seed quality assurance, and trade in seeds | Delivering Genetic Gains in Farmers’ Fields
WP1-DELIVER Facilitating the delivery of agronomy-at-scale solutions | Excellence in Agronomy for Sustainable Intensification and Climate Change Adaptation
WP1-ReFOCUS ReFOCUS Aligning breeding teams and breeding objectives with farmers’ needs | Accelerated Breeding: Meeting Farmers' Needs with Nutritious, Climate-Resilient Crops
WP1-TRANSFORM Gender transformative approaches (GTAs) | HER+: Harnessing Gender and Social Equality for Resilience in Agrifood Systems
WP3-Use Supporting breeding programs through increasing value and use of collections (Use) | Conservation and Use of Genetic Resources (Genebanks)