## Assumptions
Group by Workpackage | Assumption start point | Assumption end point | Assumption | Assumption type
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTCOME - 2.1 Breeding networks established | EOI - 1. Increased the rate of genetic gains | Raising the strategic and operational capacity of NARES-CGIAR rice breeding networks will deliver a higher rate of genetic gain, varietal uptake, and varietal replacement among small-scale farmers | Actor is empowered to act
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTCOME - 3.1 Haplotype discovery and deployment | EOI - 3. Discovery and trait deployment (TD&D) | CGIAR resources will effectively complement the project investment in rapid product development and dissemination | Actor is empowered to act
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTCOME - 4.1 Adoption of Rapid-Cycle Genomic Selection (RCGS) | EOI - 1. Increased the rate of genetic gains | CGIAR resources will effectively complement the project investment in rapid product development and dissemination | Actor is empowered to act
Work Package 5 Rapid varietal turnover | OUTCOME - 5.1 Rapid varietal turnover | EOI - 5. Policy solutions to accelerate varietal turnover | National varietal testing and release system would support the rapid varietal testing and release from CGIAR-NARES breeding network | New or improved conditions make it possible to act
Work Package 5 Rapid varietal turnover | OUTCOME - 5.1 Rapid varietal turnover | EOI - 4. Strengthened capacity of seed system actors | National varietal testing and release system would support the rapid varietal testing and release from CGIAR-NARES breeding network | New or improved conditions make it possible to act
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTCOME - 6.1 Global rice breeding program | EOI - 2. Stronger partnership models | NARES and SME partners are interested in partnering in networks with CGIAR global rice breeding program on the basis that these partnership platforms create greater innovation, efficiency, and effectiveness in the design, development, and delivery of new demand-driven varieties to low-income farmers | New or improved conditions make it possible to act
| EOI - 1. Increased the rate of genetic gains | AA - Genetic Innovation | Improved varieties based on gender-intentional product profiles will be more widely accepted since they possess the desired traits based on partner demand and market intelligence in local contexts | New or improved knowledge/technology makes it possible to act
| EOI - 2. Stronger partnership models | AA - Genetic Innovation | NARES and SME partners are interested in partnering in networks with CGIAR global rice breeding program on the basis that these partnership platforms create greater innovation, efficiency, and effectiveness in the design, development, and delivery of new demand-driven varieties to low-income farmers | New or improved conditions make it possible to act
| EOI - 4. Strengthened capacity of seed system actors | AA - Genetic Innovation | Improved varieties based on gender-intentional product profiles will be more widely accepted since they possess the desired traits based on partner demand and market intelligence in local contexts | New or improved knowledge/technology makes it possible to act
| EOI - 4. Strengthened capacity of seed system actors | AA - Genetic Innovation | National varietal testing and release system would support the rapid varietal testing and release from CGIAR-NARES breeding network. | New or improved conditions make it possible to act
| EOI - 5. Policy solutions to accelerate varietal turnover | AA - Genetic Innovation | Improved varieties based on gender-intentional product profiles will be more widely accepted since they possess the desired traits based on partner demand and market intelligence in local contexts | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Poverty Reduction, Livelihoods and Jobs | Farmers will be able to increase incomes from higher-yielding, market-demanded varieties | New or improved knowledge/technology makes it possible to act
| AA - Genetic Innovation | IA - Poverty Reduction, Livelihoods and Jobs | Farmers will be able to increase incomes from higher-yielding, market-demanded varieties | New or improved knowledge/technology makes it possible to act

## Research Questions
Work package | Output short title | Output statement | Research Question

## Scientific Methods
Work Package | Output short title | Output statement | Scientific Method

## Result Framework
WP Title | Result type (outcome or output) | Result Short title | Result Statement | Result Type | Responsible Organization | Partners | Outcome actor type | Outcome actor type of change | Outcome: Is actor a partner? | Qualitative: minimum level of success | Qualitative: moderate level of success | Qualitative: maximum level of success | Location | Country | Region | Indicator | Type | Unit of measurement | Data source | Data collection method | Data collection frequency | Location | Country | Region | Baseline value | Baseline date | Target value | Target date
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTCOME | 1.1 Breeding pipelines and objectives | Breeding pipelines and objectives aligned with farmers and consumers needs | Other | International Rice Research Institute |  | government body, private company, small and medium enterprises (SME), university, research institution | change in behavior/practice, Change in policy | Yes |  |  |  | regional |  | Sub-Saharan Africa, Southern Asia | Percentage (%) of breeding pipelines oriented towards specific market segments | Number of policies/ strategies/ laws/ regulations/ budgets/ investments/ curricula modified in design or implementation, informed by CGIAR research. | Percent |  |  |  | regional |  |  | 0 | 01/01/2024 | 10 0 | 30/04/2025 30/12/2024
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTPUT | 1.1.1 Priority market segments | Priority market segments for Africa identified and agreed upon based on the impact opportunities, especially for women and marginalized populations. | Innovation | International Rice Research Institute | [10 empty] | Number of investment cases developed for each pipeline | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 5 | 30/04/2025
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTPUT | 1.1.1 Priority market segments | Priority market segments for Africa identified and agreed upon based on the impact opportunities, especially for women and marginalized populations. | Innovation | International Rice Research Institute | [10 empty] | Number of Geographic Information System (GIS) and socio-economic characterization of each market segment including gender-disaggregated mapping of producers and consumers available in Global Market Intelligence Platform (GloMIP) | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTPUT | 1.1.1 Priority market segments | Priority market segments for Africa identified and agreed upon based on the impact opportunities, especially for women and marginalized populations. | Innovation | International Rice Research Institute | [10 empty] | Number of market segments linked to the pipelines that serve them, with market size information available in Global Market Intelligence Platform (GloMIP) | Number of innovations | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 5 | 30/04/2025
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTPUT | 1.1.2 Gender-intentional product concepts | Gender-intentional product concepts in each market segment developed and biennially updated using Market Intelligence (MI) Standard Operation Procedures (SOPs). | Innovation | International Rice Research Institute | Bill & Melinda Gates Foundation | [9 empty] | Number of transdisciplinary teams established | Number of teams | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTPUT | 1.1.2 Gender-intentional product concepts | Gender-intentional product concepts in each market segment developed and biennially updated using Market Intelligence (MI) Standard Operation Procedures (SOPs). | Innovation | International Rice Research Institute | Bill & Melinda Gates Foundation | [9 empty] | Number of strategy to ensure gender intentionality in product concept design adapted from Market Intelligence (MI) Standard Operating Procedures (SOPs) | Number of strategy | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTPUT | 1.1.2 Gender-intentional product concepts | Gender-intentional product concepts in each market segment developed and biennially updated using Market Intelligence (MI) Standard Operation Procedures (SOPs). | Innovation | International Rice Research Institute | Bill & Melinda Gates Foundation | [9 empty] | Number of gender-intentional product concepts developed and validated for each priority market segment and made available in Breeding Portal (BP) and Global Market Intelligence Platform (GloMIP) | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTPUT | 1.1.3 Breeding effort size | Breeding effort size tailored to be commensurate with market segment and impact opportunities, with biennial updates | Capacity | International Rice Research Institute | [10 empty] | Number of leveraged market segments mapped, and effort quantified | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 1 Breeding pipelines and objectives aligned with farmers needs | OUTPUT | 1.1.3 Breeding effort size | Breeding effort size tailored to be commensurate with market segment and impact opportunities, with biennial updates | Capacity | International Rice Research Institute | [10 empty] | Number of breeding pipeline size specified for each priority market segment | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTCOME | 2.1 Breeding networks established | National Agricultural Research and Extention Systems (NARES)- CGIAR breeding networks established and strengthened | Capacity | International Rice Research Institute |  | government body, private company, small and medium enterprises (SME), university, research institution | change in knowledge, change in skills, change in relationship | Yes |  |  |  | regional |  | Sub-Saharan Africa, Southern Asia | Percentage (%) of breeding pipelines using improved organizational framework, motivated and empowered teams; transparent, metrics-driven, learning and evaluation | Number of policies/ strategies/ laws/ regulations/ budgets/ investments/ curricula modified in design or implementation, informed by CGIAR research. | Percent |  |  |  | regional |  |  | 0 | 01/01/2024 | 10 0 | 30/04/2025 30/12/2024
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.1 Network governance structures | Network Governance Structures, including formal roles and responsibilities for National Agricultural Research and Extension System (NARES), using best practices as provided by Accelerated Breeding Initiative (ABI)-Transform and other networks implemented by IRRI and AfricaRice | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of network governance mechanism defined and implemented | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.1 Network governance structures | Network Governance Structures, including formal roles and responsibilities for National Agricultural Research and Extension System (NARES), using best practices as provided by Accelerated Breeding Initiative (ABI)-Transform and other networks implemented by IRRI and AfricaRice | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Amount of funds allocated to partners programs in Sub-Saharan Africa | Amount of funds | US Dollar |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.2 Baseline assessment and customized improvement plans | Reports on baseline assessment completed and Customized Improvement Plans (Capacity Development Plans) for National Agricultural Research and Extension System (NARES) network partners for breeding modernization developed and implemented | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Proportion of the NARES for whom baseline assessements have been completed | Number of partners | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 50 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.2 Baseline assessment and customized improvement plans | Reports on baseline assessment completed and Customized Improvement Plans (Capacity Development Plans) for National Agricultural Research and Extension System (NARES) network partners for breeding modernization developed and implemented | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Proportion of NARES partners who have developed and implemented Customized Improvement Plans | Number of partners | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 25 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.3 Data-driven product advancement | Implementing and institutionalizing best practices in the National Agricultural Research and Extension System (NARES) network in line testing towards data-driven product advancement | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of trials per target population of environments (TPEs) | Number of trials | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.3 Data-driven product advancement | Implementing and institutionalizing best practices in the National Agricultural Research and Extension System (NARES) network in line testing towards data-driven product advancement | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of network lines advanced to national release testing in each partner NARES | Number of network lines | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.3 Data-driven product advancement | Implementing and institutionalizing best practices in the National Agricultural Research and Extension System (NARES) network in line testing towards data-driven product advancement | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Percentage accuracy (combined analysis) of Stage 1 and later-stage trials successfully implemented by each partner (minimum accuracy of 0.5) | Accuracy | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 50 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.3 Data-driven product advancement | Implementing and institutionalizing best practices in the National Agricultural Research and Extension System (NARES) network in line testing towards data-driven product advancement | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of NARES programs supporting network-derived lines in national release testing | Number of programs | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.3 Data-driven product advancement | Implementing and institutionalizing best practices in the National Agricultural Research and Extension System (NARES) network in line testing towards data-driven product advancement | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of tricot-style on-farm trials conducted in each partner country | Number of trials | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.4 Joint product advancements | Joint product advancements with a view to National Agricultural Research and Extension System (NARES) taking full ownership of late stage/local advancements | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of lines advanced into national product testing (NPT) and on-farm testing (OFT) in each country | Number of lines | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.4 Joint product advancements | Joint product advancements with a view to National Agricultural Research and Extension System (NARES) taking full ownership of late stage/local advancements | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of crop tour and advancement meetings organized jointly with NARES and CGIAR to decide on the stage 1 and stage 2 product advancement. | Number of tours/meetings | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.4 Joint product advancements | Joint product advancements with a view to National Agricultural Research and Extension System (NARES) taking full ownership of late stage/local advancements | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of NARES partners actively participating in late-stage product advancement process | Number of partners | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.5 Phenotyping and genotyping services | Ensured phenotyping and genotyping services support the National Agricultural Research and Extension System (NARES)-CGIAR network including biotic and abiotic stress network screening together with the NARES | Capacity | International Rice Research Institute | [10 empty] | Number of materials/samples phenotyped and genotyped with assisted by BRI | Number of materials | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.5 Phenotyping and genotyping services | Ensured phenotyping and genotyping services support the National Agricultural Research and Extension System (NARES)-CGIAR network including biotic and abiotic stress network screening together with the NARES | Capacity | International Rice Research Institute | [10 empty] | Number of NARES-CGIAR partners joined and benefited from the network | Number of partners | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 2 NARES-CGIAR breeding networks established and strengthened | OUTPUT | 2.1.5 Phenotyping and genotyping services | Ensured phenotyping and genotyping services support the National Agricultural Research and Extension System (NARES)-CGIAR network including biotic and abiotic stress network screening together with the NARES | Capacity | International Rice Research Institute | [10 empty] | Number of formal networks for the biotic and abiotic stress phenotyping | Number of network | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTCOME | 3.1 Haplotype discovery and deployment | Breeding programs have improved access to support on haplotype discovery/validation and deployment | Capacity | International Rice Research Institute | Africa Rice Center | government body, private company, small and medium enterprises (SME), university, research institution |  | Yes |  |  |  | regional |  | Southern Asia, Sub-Saharan Africa | Number of breeding programs supported by haplotype discovery/validation and deployment | Change in the capacity of key (a) Individuals, (b) Organizations (government, civil society and private sector), and (c) Networks (e.g. multi-stakeholder platforms). | Number |  |  |  | regional |  |  | 0 | 01/08/2024 | 1 0 | 30/04/2025 30/12/2024
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.1 Trait and haplotype priorities | Trait and haplotype priorities established (biotic and abiotic) for African breeding pipelines, and key genes made available in elite donors to augmentation pipeline | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Deployment and trait development activities carried out according to QC criteria in the trait development pipeline | Number of activities | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.1 Trait and haplotype priorities | Trait and haplotype priorities established (biotic and abiotic) for African breeding pipelines, and key genes made available in elite donors to augmentation pipeline | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Status of each trait mapped to the trait development pipeline | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.1 Trait and haplotype priorities | Trait and haplotype priorities established (biotic and abiotic) for African breeding pipelines, and key genes made available in elite donors to augmentation pipeline | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Trait prioritization framework established | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.1 Trait and haplotype priorities | Trait and haplotype priorities established (biotic and abiotic) for African breeding pipelines, and key genes made available in elite donors to augmentation pipeline | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Frequency of major genes/QTLs assessed in IRRI and AfricaRice core material | Number of major genes | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.2 Genes for African breeding pipelines | Key genes for African breeding pipelines upscaled in frequency and made available in diverse elite backgrounds through the line augmentation process. | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Pyramids of priority genes created from deployment products to act as donors in augmentation process | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.2 Genes for African breeding pipelines | Key genes for African breeding pipelines upscaled in frequency and made available in diverse elite backgrounds through the line augmentation process. | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of genes identified for augmentation | Number of genes | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 3 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.2 Genes for African breeding pipelines | Key genes for African breeding pipelines upscaled in frequency and made available in diverse elite backgrounds through the line augmentation process. | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Recipient lines nominated by breeding programs augmented with priority genes, targeting 3 genes for each round of augmentation | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.3 Resource platforms | Resource platforms curated to document elite donors created and made available to breeders, with associated quality control (QC) metrics of introgression | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Shared information resource maintained with availability of key genes, including recipient background and introgression metrics. | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.4 Prioritized haplotypes monitored | Frequency of prioritized haplotypes monitored in breeding programs to ensure increasing frequency. | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Frequency of major genes/QTLs reported annually in crossing blocks and stage 1 and 2 advancements | Number of genes | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.5 Marker assisted selection analytics | Enterprise Breeding System (EBS) supported marker assisted selection analytics and introgression workflows | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Molecular analytics support established within EBS | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 3 Haplotype discovery/validation and deployment pipeline | OUTPUT | 3.1.5 Marker assisted selection analytics | Enterprise Breeding System (EBS) supported marker assisted selection analytics and introgression workflows | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Introgression workflows fully digitalized in the EBS system; introgression activities 100% encoded in EBS | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 100 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTCOME | 4.1 Adoption of Rapid-Cycle Genomic Selection (RCGS) | CG-National Agricultural Research and Extension System (NARES) breeding networks adopt Rapid-Cycle Genomic Selection (RCGS) as a breeding tool | Innovation | International Rice Research Institute | Africa Rice Center | government body, private company, small and medium enterprises (SME), university, research institution | change in skills, change in behavior/practice | Yes |  |  |  | regional |  | Southern Asia, Sub-Saharan Africa | Percentage of breeding pipelines supposed by a dedicated TD&D program | Change in the capacity of key (a) Individuals, (b) Organizations (government, civil society and private sector), and (c) Networks (e.g. multi-stakeholder platforms). | Percent |  |  |  | regional |  |  | 0 | 01/01/2024 | 10 0 | 30/04/2025 30/12/2024
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.1 Simulation-validated Rapid-Cycle Genomic Selection (RCGS) pipeline | Simulation-validated Rapid-Cycle Genomic Selection (RCGS) pipeline designs and implementation plan including deadlines formalized | Information product | International Rice Research Institute | [10 empty] | Cycle time calculated at the crossing block stage for all breeding pipelines | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.1 Simulation-validated Rapid-Cycle Genomic Selection (RCGS) pipeline | Simulation-validated Rapid-Cycle Genomic Selection (RCGS) pipeline designs and implementation plan including deadlines formalized | Information product | International Rice Research Institute | [10 empty] | Number of simulations carried out to optimize breeding pipelines | Number of simulations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.10 Leveraging breeding investment | Identified market segments where existing breeding investment could be leveraged. | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of market segments and pipelines matched | Number of market segments | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.10 Leveraging breeding investment | Identified market segments where existing breeding investment could be leveraged. | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Genetic correlations between pipelines | Genetic correlations | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 10 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.2 Predicted genetic gain | Predicted genetic gain reported for each population improvement program, based on data from Stage 1 trials for breeder’s equation components: cycle time, accuracy, and selection intensity | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Cycle time calculated at the crossing block, accuracy at parental selection stage, and selection intensity and accuracy of selection for complex traits | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.3 Selection indices and optimal crossing | Implemented selection indices and optimal crossing approaches for cross/parent selection | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of pipelines using the desired gains index in practice | Number of pipelines | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.3 Selection indices and optimal crossing | Implemented selection indices and optimal crossing approaches for cross/parent selection | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of pipelines using the sparse testing and number of farms or research stations where testing happens | Number of pipelines | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.4 State-of-art genetic evaluation methods | Implemented state-of-art genetic evaluation methods (sparse testing with genomic relationship matrix, large increase in the number of stage 1 trials, use of stress environment) and associated analytical pipelines | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Genetic standard deviations annually achieved for yield in Stage 1 calculated in predicted genetic gain | Genetic standard deviations | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.5 On-farm Genomic Selection | On-farm Genomic Selection (GS) testing approach evaluated in the upland rice pipeline | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of farms and selection candidates included in on-farm Genomic Selection (GS) trials | Number of farms | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.5 On-farm Genomic Selection | On-farm Genomic Selection (GS) testing approach evaluated in the upland rice pipeline | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of parents from population improvement program used in product development by partners | Number of parents | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 25 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.5 On-farm Genomic Selection | On-farm Genomic Selection (GS) testing approach evaluated in the upland rice pipeline | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Landmark paper on the on-farm testing made jointly with ABI team | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.6 Genetic correlation | Calculated genetic correlation between on-farm and on-station testing in Sub-Saharan Africa (SSA) | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Genetic correlation values | Genetic correlation values | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.7 Genetic correlation between additive breeding values | Calculated genetic correlation between additive breeding values estimated from male vs female managed plots and between plots in favorable environments and those heavily affected by abiotic and biotic stresses - drought, flooding, salinity, iron toxicity, weed pressure, low fertility, and pests and diseases. | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Genetic correlation values | Genetic correlation values | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.8 Realized genetic gain from on-farm trials | Compute realized genetic gain from on-farm trials in target population of environments (TPEs) by modifying the On-Farm Trial (OFT) design to include major varieties developed by CGIAR-National Agricultural Research and Extension System (NARES) breeding programs | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Percentage of realized genetic gain on farm trials | Genetic gain | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 1.5 | 30/04/2025
Work Package 4 CG-NARES breeding networks adopt rapid-cycle genomic selection (RCGS) as a breeding tool | OUTPUT | 4.1.9 On-farm testing approach findings | Disseminated findings of the on-farm testing approach implemented in 4.5. and genetic correlations calculated in 4.6 and 4.7 | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of communication workshop in the new testing approaches carried | Number of people trained, long-term (including Masters and PhDs) and short-term, disaggregated by gender | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTCOME | 5.1 Rapid varietal turnover | Rapid varietal turnover that aligns with and complements SeedEqual efforts | Other | International Rice Research Institute | Africa Rice Center | Farmers, Farmers’ associations | change in attitude, change in skills, change in behavior/practice | Yes |  |  |  | regional |  | Southern Asia, Sub-Saharan Africa | Quantity of seed produced and certified for a prioritized set of representative crops and countries | Other quantitative measure of CGIAR innovation use (e.g. area) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 0 | 30/04/2025 30/12/2024
Work Package 5 Rapid varietal turnover | OUTCOME | 5.1 Rapid varietal turnover | Rapid varietal turnover that aligns with and complements SeedEqual efforts | Other | International Rice Research Institute | Africa Rice Center | Farmers, Farmers’ associations | change in attitude, change in skills, change in behavior/practice | Yes |  |  |  | regional |  | Southern Asia, Sub-Saharan Africa | Weighted average varietal age (WAVA) in farmers’ fields for a prioritized set of representative crops and countries | Other quantitative measure of CGIAR innovation use (e.g. area) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 10 0 | 30/04/2025 30/12/2024
Work Package 5 Rapid varietal turnover | OUTCOME | 5.1 Rapid varietal turnover | Rapid varietal turnover that aligns with and complements SeedEqual efforts | Other | International Rice Research Institute | Africa Rice Center | Farmers, Farmers’ associations | change in attitude, change in skills, change in behavior/practice | Yes |  |  |  | regional |  | Southern Asia, Sub-Saharan Africa | Seed Replacement Rate (the percentage of area sown out of the total area of crop planted in the season by using certified/quality seeds other than the farm saved seed) | Other quantitative measure of CGIAR innovation use (e.g. area) | Percent |  |  |  | regional |  |  | 0 | 01/01/2024 | 10 0 | 30/04/2025 30/12/2024
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.1 Profiling of the popular and farmer-grown varieties | Detailed profiling of the popular/ farmer-grown varieties across prioritized market segments and list of current varieties to be replaced | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Country and market segment-wise master file (along with profiling including the quality profile, area covered/ seed produced, age) of the popular/ farmer-grown varieties prepared | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.1 Profiling of the popular and farmer-grown varieties | Detailed profiling of the popular/ farmer-grown varieties across prioritized market segments and list of current varieties to be replaced | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Top 1-2 "replacement targets" (varieties) identified per market segment (country-wise) for the priority market segments | Number of varieties | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 22 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.2 Performance of test candidate varieties | Performance of test candidate varieties in large-scale on-farm trials evaluated in close collaboration with National Agricultural Research and Extension System (NARES) and other partners. | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Heritability of agronomic traits in scaled on-farm trials | Heritibality | Percentage |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.2 Performance of test candidate varieties | Performance of test candidate varieties in large-scale on-farm trials evaluated in close collaboration with National Agricultural Research and Extension System (NARES) and other partners. | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of on-farm trial (OFTs) conducted by the seed network in target market segments | Number of on-farm trials | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.2 Performance of test candidate varieties | Performance of test candidate varieties in large-scale on-farm trials evaluated in close collaboration with National Agricultural Research and Extension System (NARES) and other partners. | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Statistically valid unified on-farm tiral (OFT) strategy | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.2 Performance of test candidate varieties | Performance of test candidate varieties in large-scale on-farm trials evaluated in close collaboration with National Agricultural Research and Extension System (NARES) and other partners. | Capacity | International Rice Research Institute | Africa Rice Center | [9 empty] | Digitised and good quality on-farm trial (OFT) data | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.3 Potential candidate varieties | List of potential candidate varieties to replace existing ones, detailed product description and varietal replacement case for potential candidate varieties | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Detailed One Page Profiles (OPP) for all the varieties to be introduced in the prioritised market segments developed and available in GloMIP | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 33 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.3 Potential candidate varieties | List of potential candidate varieties to replace existing ones, detailed product description and varietal replacement case for potential candidate varieties | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Top 1-2 new varieties per prioritised market segment per country identified to be introduced. | Number of varieties | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 22 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.3 Potential candidate varieties | List of potential candidate varieties to replace existing ones, detailed product description and varietal replacement case for potential candidate varieties | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of field demonstrations and field days conducted in target market segments in coordination with the seed network partners | Number of activities | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 55 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.3 Potential candidate varieties | List of potential candidate varieties to replace existing ones, detailed product description and varietal replacement case for potential candidate varieties | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Country-wise master file of the new varieties as per market segments and matching product concepts prepared | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.3 Potential candidate varieties | List of potential candidate varieties to replace existing ones, detailed product description and varietal replacement case for potential candidate varieties | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Varietal replacement criteria defined | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.3 Potential candidate varieties | List of potential candidate varieties to replace existing ones, detailed product description and varietal replacement case for potential candidate varieties | Information product | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of demonstration activities carried out by the network in coordination with NARES | Number of activities | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 33 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.4 Varietal licensing models | Facilitating varietal licensing models development; and plans for seed production for new products developed and implemented in partnership with the seed chain stakeholders | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Quantity of seeds (breeders' and/or certified) produced and disseminated through the networks | Quantity of seeds | Kilograms |  |  |  | global |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.4 Varietal licensing models | Facilitating varietal licensing models development; and plans for seed production for new products developed and implemented in partnership with the seed chain stakeholders | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | SeedCast/ Similar (in alignment with Seed Equal) App to be rolled out in target counties in Africa | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 2 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.4 Varietal licensing models | Facilitating varietal licensing models development; and plans for seed production for new products developed and implemented in partnership with the seed chain stakeholders | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Types of varietal licensing models facilitated | Number of innovations | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 5 Rapid varietal turnover | OUTPUT | 5.1.4 Varietal licensing models | Facilitating varietal licensing models development; and plans for seed production for new products developed and implemented in partnership with the seed chain stakeholders | Innovation | International Rice Research Institute | Africa Rice Center | [9 empty] | Number of capacity building trainings/ initiatives conducted in the prioritised countries | Number of people trained, long-term (including Masters and PhDs) and short-term, disaggregated by gender | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTCOME | 6.1 Global rice breeding program | A global rice breeding program established across Internation Rice Research Institute (IRRI), AfricaRice, and International Center for Tropical Agriculture (CIAT) under the auspices of Genetic Innovations | Innovation | International Rice Research Institute | Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT), Africa Rice Center | research institution | change in behavior/practice, Change in policy | Yes |  |  |  | global |  |  | Proportion of NARES-CGIAR-SME breeding networks that have developed systems to measure adoption (with sex and age aggregation, using innovative and lower cost systems) | Other quantitative measure of CGIAR innovation use (e.g. area) | Percent |  |  |  | global |  |  | 0 | 01/01/2024 | 10 0 | 30/04/2025 30/12/2024
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.1 Global framework for rice breeding | A global framework of rice market segments, breeding pipelines and product concepts established to serve as the foundation for a global rice breeding effort under a common governance system, including planning, programming, and progress reporting. | Innovation | International Rice Research Institute | Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT), Africa Rice Center | [9 empty] | A governance structure established | Number of innovations | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.1 Global framework for rice breeding | A global framework of rice market segments, breeding pipelines and product concepts established to serve as the foundation for a global rice breeding effort under a common governance system, including planning, programming, and progress reporting. | Innovation | International Rice Research Institute | Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT), Africa Rice Center | [9 empty] | A set of breeding pipelines with clealry defined product concepts mapped to serve the prioritized global markets segments developed with in the first six months of the launch of the program | Number of pipeline | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.1 Global framework for rice breeding | A global framework of rice market segments, breeding pipelines and product concepts established to serve as the foundation for a global rice breeding effort under a common governance system, including planning, programming, and progress reporting. | Innovation | International Rice Research Institute | Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT), Africa Rice Center | [9 empty] | A common language and vocabulary adopted | Number of other information products/data assets (including: reports, briefs, extension, training and e-learning content and other materials, books and book chapters, data and databases, data collection and analysis tools (e.g. models and survey tools), video, audio and images, graphics, maps, and other GIS outputs, computer software, models and code, digital and mobile applications, and web-based services (e.g. websites, data portals, online platforms) | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.2 OneRice breeding strategy | Adoption of OneRice breeding strategy by the participating centers specifically focused on an integrated population improvement, haplotype mobilization, and product extraction program. | Innovation | International Rice Research Institute | Africa Rice Center, Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT) | [9 empty] | All the breeding pipelines across three centres adopt the One Rice breeding strategy with needed customization | Number of pipeline | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.2 OneRice breeding strategy | Adoption of OneRice breeding strategy by the participating centers specifically focused on an integrated population improvement, haplotype mobilization, and product extraction program. | Innovation | International Rice Research Institute | Africa Rice Center, Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT) | [9 empty] | Efforts size determined for every breeding pipeline in proportion to the impact opportunity in the market served | Number of pipeline | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.2 OneRice breeding strategy | Adoption of OneRice breeding strategy by the participating centers specifically focused on an integrated population improvement, haplotype mobilization, and product extraction program. | Innovation | International Rice Research Institute | Africa Rice Center, Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT) | [9 empty] | In alignment with Genetic Inovation Process Management Team, adopt the QMS and respective audit mechanisms for improvement | Adoption | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 1 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.3 Defined responsibilities and division of labor | Clearly defined responsibilities and division of labor among CGIAR (International Rice Research Institute, AfricaRice, International Center for Tropical Agriculture, and Genetic Innovation) and National Agricultural Research and Extension System (NARES) partners established for prioritized breeding networks of the pipelines. | Capacity | International Rice Research Institute | Africa Rice Center, Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT) | [9 empty] | Every researcher's role and responsibilities clearly defined for each of the breeding pipelines | Number of breeding pipelines | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.3 Defined responsibilities and division of labor | Clearly defined responsibilities and division of labor among CGIAR (International Rice Research Institute, AfricaRice, International Center for Tropical Agriculture, and Genetic Innovation) and National Agricultural Research and Extension System (NARES) partners established for prioritized breeding networks of the pipelines. | Capacity | International Rice Research Institute | Africa Rice Center, Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT) | [9 empty] | Researchers assigned appropriately to each of the breeding pipelines as per their skills sets, comptetencies and location | Number of breeding pipelines | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.4 Research data management platform | Research data management platform (Enterprise Breeding System deployment) and centralized services coordinated through BR (genotyping, mechanization support, and phenotyping for critical product concept traits) adopted by all the three participating centers | Capacity | International Rice Research Institute | Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT), Africa Rice Center | [9 empty] | Breeding pipelines/programs routinely access use the centralized services offered through BRI genotyping, drone phenotyping, mechanization etc | Number of breeding pipelines | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 11 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.5 Resourcing and leveraging strategy and plan | A resourcing and leveraging strategy and plan developed to create a level playing field for all participating centers, focusing on germplasm exchange across the centers, research capacity, funding, and experiences in breeding program management | Innovation | International Rice Research Institute | Africa Rice Center, Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT) | [9 empty] | Critical gaps identified in the breeding capacity and resources of all the three centres | Number of centers | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 3 | 30/04/2025
Work Package 6 A global rice breeding program established across IRRI, AfricaRice, and CIAT under the auspices of Genetic Innovations (Transition Plan) | OUTPUT | 6.1.5 Resourcing and leveraging strategy and plan | A resourcing and leveraging strategy and plan developed to create a level playing field for all participating centers, focusing on germplasm exchange across the centers, research capacity, funding, and experiences in breeding program management | Innovation | International Rice Research Institute | Africa Rice Center, Alliance of Bioversity International & the International Center for Tropical Agriculture (CIAT) | [9 empty] | A strategy and plan developed to fill these gaps - manpower & skills, resources to create level playing field for the centres | Number of innovations | Number |  |  |  | global |  |  | 0 | 01/01/2024 | 1 | 30/04/2025

## EOI-O
EOI-O title | EOI-O Statement | Outcome Type | Responsible Organization | Partners | Actor type | Actor type of change | Is actor a partner? | Qualitative: minimum level of success | Qualitative: moderate level of success | Qualitative: maximum level of success | Location | Country | Region | Indicator | Type | Unit of measurement | Data source | Data collection method | Data collection frequency | Location | Country | Region | Baseline value | Baseline date | Target value | Target date
1. Increased the rate of genetic gains | CGIAR-NARES-SME breeding pipelines have increased the rate of genetic gains, providing seed system actors with farmer-preferred candidate varieties with step change in performance under farmers conditions. | capacity | International Rice Research Institute | Africa Rice Center | government body, small and medium enterprises (SME), research institution | change in knowledge, change in skills, change in behavior/practice | Yes |  |  |  | regional |  | Sub-Saharan Africa, Southern Asia | Percentage of breeding pipelines that have increased the rate of genetic gains in the form of farmer-preferred varieties | Change in the capacity of key (a) Individuals, (b) Organizations (government, civil society and private sector), and (c) Networks (e.g. multi-stakeholder platforms). | Percent |  |  |  | regional |  |  | 0 | 01/01/2024 | 70 0 | 30/04/2025 30/12/2024
2. Stronger partnership models | CGIAR-NARES-SME breeding networks implement stronger partnership models where NARES and SMEs have increased contribution to the breeding process | capacity | International Rice Research Institute | Africa Rice Center | government body, small and medium enterprises (SME), research institution | change in relationship, change in behavior/practice | Yes |  |  |  | regional |  | Sub-Saharan Africa, Southern Asia | Percentage of CGIAR-NARES-SME breeding network implementing stronger partnership models | Change in the capacity of key (a) Individuals, (b) Organizations (government, civil society and private sector), and (c) Networks (e.g. multi-stakeholder platforms). | Percent |  |  |  | regional |  |  | 0 | 01/01/2024 | 80 0 | 30/04/2025 30/12/2024
3. Discovery and trait deployment (TD&D) | CGIAR-NARES breeding pipelines are supported by discovery and trait deployment (TD&D) programs that deliver high impact traits within elite parental lines | capacity | International Rice Research Institute | Africa Rice Center | government body, small and medium enterprises (SME), research institution | change in skills, change in behavior/practice | Yes |  |  |  | regional |  | Southern Asia, Sub-Saharan Africa | Percentage of breeding pipelines supported by a dedicated TD&D program | Change in the capacity of key (a) Individuals, (b) Organizations (government, civil society and private sector), and (c) Networks (e.g. multi-stakeholder platforms). | Percent |  |  |  | regional |  |  | 0 | 01/01/2024 | 50 0 | 30/04/2025 30/12/2024
4. Strengthened capacity of seed system actors | Seed systems actors, such as seed companies and other seed multipliers' (including farmer-based seed actors) capacities are strengthened to produce and deliver increased quantities of quality seed of improved varieties for representative crops and geographies | capacity | International Rice Research Institute | Africa Rice Center | private company, small and medium enterprises (SME), Farmers’ associations | change in skills, change in behavior/practice | Yes |  |  |  | regional |  | Sub-Saharan Africa, Southern Asia | Number of seed system actors with increased capacities to produce and deliver increased quantities of quality seed of improved varieties | Change in the capacity of key (a) Individuals, (b) Organizations (government, civil society and private sector), and (c) Networks (e.g. multi-stakeholder platforms). | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 1 0 | 30/04/2025 30/12/2024
5. Policy solutions to accelerate varietal turnover | Government partners in public policy design and implementation actively promote policy solutions to accelerate varietal turnover, adoption and quality seed use. | Number of stakeholders that have used FCM evidence, learning and guidance to inform crisis prevention and preparedness, anticipatory or early action, and disaster risk reduction along the HDP nexus | International Rice Research Institute | Africa Rice Center | policymaker, government body, research institution | change in attitude, Change in policy | Yes |  |  |  | regional |  | Southern Asia, Sub-Saharan Africa | Number of policy solutions to accelerate varietal turnover, adoption and quality seed use as produced/advocated by government partners | Number of policies/ strategies/ laws/ regulations/ budgets/ investments/ curricula modified in design or implementation, informed by CGIAR research. | Number |  |  |  | regional |  |  | 0 | 01/01/2024 | 2 0 | 30/04/2025 30/12/2024

## AA-O
Action Area | Outcome | Indicator | Description
Genetic Innovation | CGIAR partners develop and scale innovations that contribute to the empowerment of women and other social groups in food, land, and water systems. | GIi 4.1 - Proportion of CGIAR-NARS-SME networks that have developed systems to measure adoption of innovations with gender implications (with sex and age disaggregation, using innovative and lower cost systems).
Genetic Innovation | National and private seed company breeding programs accelerate the development of varieties that provide larger scale benefits across the 5 Impact Areas. | undefined - Realized genetic gains in farmer-relevant conditions., undefined - Proportion of pipelines that have implemented systems to measure predicted and realized genetic gains on farm.
Genetic Innovation | Integrated seed systems increase the quantity of quality seed of improved varieties available to farmers for priority crops and in selected countries, geographies, and market segments | STRAFSGIi 1.2 - Change in Weighted average varietal age (WAVA) in famers’ fields for a prioritized set of representative crops and countries., undefined - Quantity of quality seed produced and certified for a prioritized set of representative crops and countries.
Genetic Innovation | Research institutions, government analytical units, and scaling partners in the Global South have improved knowledge, skills, access to data, capacity to develop tools, innovations, and undertake research to support transformation of food, land and water systems contributing to livelihood, inclusion, nutrition, environmental and climate objectives. | STi 4.1 - External users, particularly NARS, increasingly access crop diversity.
Genetic Innovation | CGIAR-NARS-SME networks use market segments, target product profiles to orient variety development and deployment towards those that provide larger scale benefits across the 5 Impact Areas. | STRAFSGIi 1.1 - Proportion of new released varieties developed in alignment with market intelligence-informed target product profiles and tailored to market segments in the Global South., RAFSi 3.1 - Proportion of CGIAR-NARS-SME breeding pipelines within CGIAR-NARS-SME network using market segments, target product profiles to guide selection decisions for all advancement steps.

## IA
IA | Global Target | Indicator | Description
Climate Adaptation and Mitigation | Equip 500 million small-scale producers to be more resilient to climate shocks, with climate adaptation solutions available through national innovation systems. | #people benefiting from climate-adapted innovations
Environmental Health and Biodiversity | Maintain the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species, including through soundly managed genebanks at the national, regional, and international levels. | #ha under improved management
Gender Equality, Youth and Social Inclusion | Close the gender gap in rights to economic resources, access to ownership and control over land and natural resources for over 500 million women who work in food, land and water systems. | #youth benefiting fromrelevant CGIAR innovations, #women benefiting from relevant CGIAR innovations
Nutrition, Health and Food Security | End hunger for all and enable affordable healthy diets for the 3 billion people who do not currently have access to safe and nutritious food. | #people benefiting from relevant CGIAR innovations
Poverty Reduction, Livelihoods and Jobs | Lift at least 500 million people living in rural areas above the extreme poverty line of US $1.90 per day (2011 PPP). | #people assisted to exit poverty

## SDG
SDG | Target | Description
1 - End poverty in all its forms everywhere | 1.1 By 2030, eradicate extreme poverty for all people everywhere, currently measured as people living on less than $1.25 a day, 1.5 By 2030, build the resilience of the poor and those in vulnerable situations and reduce their exposure and vulnerability to climate-related extreme events and other economic, social and environmental shocks and disasters, 1.4 By 2030, ensure that all men and women, in particular the poor and the vulnerable, have equal rights to economic resources, as well as access to basic services, ownership and control over land and other forms of property, inheritance, natural resources, appropriate new technology and financial services, including microfinance
2 - End hunger, achieve food security and improved nutrition and promote sustainable agriculture | 2.3 By 2030, double the agricultural productivity and incomes of small-scale food producers, in particular women, indigenous peoples, family farmers, pastoralists and fishers, including through secure and equal access to land, other productive resources and inputs, knowledge, financial services, markets and opportunities for value addition and non-farm employment, 2.1 By 2030, end hunger and ensure access by all people, in particular the poor and people in vulnerable situations, including infants, to safe, nutritious and sufficient food all year round, 2.5 By 2020, maintain the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species, including through soundly managed and diversified seed and plant banks at the national, regional and international levels, and promote access to and fair and equitable sharing of benefits arising from the utilization of genetic resources and associated traditional knowledge, as internationally agreed

## Other initiatives
Work Package | Other initiative name | Other initiative Work package name
Work Package 1 Demand-driven cereal seed systems | Delivering Genetic Gains in Farmers’ Fields
Work Package 2 Target Product Profile Design | Market Intelligence and Product Profiling
Work Package 3 Behavioral Intelligence | Market Intelligence and Product Profiling
Work Package 4 Partnerships, capacity building, and coordination to ensure uptake of public-bred varieties and other innovations. | Delivering Genetic Gains in Farmers’ Fields
Work Package 4 Pipeline Investment Cases | Market Intelligence and Product Profiling
Work Package 4 SMARTER USE OF MORE DATA | Breeding Resources
Work Package 5 INNOVATION DEVELOPMENT AND RESEARCH EXCHANGE (Idare) | Breeding Resources
Work Package 5 Policies for varietal turnover, seed quality assurance, and trade in seeds | Delivering Genetic Gains in Farmers’ Fields
WP1-ReFOCUS ReFOCUS Aligning breeding teams and breeding objectives with farmers’ needs | Accelerated Breeding
WP3-TRANSFORM TRANSFORM towards inclusive, impactful CGIAR-NARES-SME breeding networks | Accelerated Breeding
WP4-DISCOVER DISCOVER: Trait Discovery and Deployment | Accelerated Breeding